HONEST 4-MONTH REALITY-CHECK TIMELINE

Project GeoGovGadget — Smart India Hackathon 2026
Team: INFERICS | Problem Statement ID: 26012

This timeline tracks the real-world execution of the GeoGovGadget 4-month sprint. It transparently contrasts theoretical hackathon deliverables against actual technical progress, hardware bottlenecks, and data constraints.

| Phase & Timeframe | Proposed Plan (What's Claimed) | Actual Execution (What's Done) | Engineering Reality & Risk Mitigation |
| --- | --- | --- | --- |
| Month 1: Setup & Data Pipelines | • Full access to high-res drone imagery & SVAMITVA/DILRMP datasets. • Complete OpenCV & GDAL ingestion pipelines ready. | • Baseline public satellite/open drone datasets ingested. • OpenCV normalization & standard raster cropping pipelines built. | • Bottleneck: Proprietary government survey data takes time to access. • Fix: Synthetic data augmentation & public GIS data bootstrapping. |
| Month 2: Core AI & Edge Prototype | • Fully trained U-Net/Mask R-CNN models running offline on Raspberry Pi. • 100% automated vector boundary extraction. | • U-Net segmentation core functional on GPU. • Basic vector conversion working. • Quantized TFLite running on Raspberry Pi for simple scenes. | • Bottleneck: Pi thermal throttling & RAM limits on ultra-high-res rasters. • Fix: Dynamic tiling (patch-based inference) & model pruning. |
| Month 3: Web-GIS & Field Testing | • Production-grade Web-GIS portal deployed across active ULBs. • Seamless zero-connectivity drone edge processing. | • Web-GIS dashboard functional for baseline polygon review & manual correction. • Simulated offline field tests on local edge nodes. | • Bottleneck: Irregular Indian urban density causes overlapping vector boundaries. • Fix: Confidence scoring & human-in-the-loop manual review interface. |
| Month 4: Refinement & Pilot Delivery | • Complete end-to-end automated deployment across municipal bodies. • Fully autonomous boundary extraction engine. | • Functional MVP complete with Web-GIS & edge deployment pipeline. • Retrained models with edge-case corrections. | • Reality: Automated cadastral mapping requires human verification by law. • Fix: Position system as an operational accelerator (months → weeks). |